## Stakeholders
Name | Team | Project Role | Department | Role | Email | Phone | Responsibility

## Vendor Quotes_old (hidden)
Price Comparison
IdentiSys
QTY | DESCRIPTION | UNIT PRICE | TOTAL PRICE | Quote Exp | PROS | CONS
40000 | Printed ISO PVC 35-bit | 1.97 | 78800 | 2023-09-13 | printed price, starting sequence 0-1,048,000 | not compatible with scanners that have 26-bit software
1 | Shipping | 200 | 200
QTY | DESCRIPTION | UNIT PRICE | TOTAL PRICE
40000 | ISO PVC 35-bit | 1.5 | 60000 | 2023-09-13 | cost per card, starting sequence 0-1,048,000 | not compatible with scanners that have 26-bit software
1 | Shipping | 200 | 200
QTY | DESCRIPTION | UNIT PRICE | TOTAL PRICE
50000 | Mifare DESFire EV3 | 2.6 | 130000 | 2023-06-30 | Alternative to LEAF | Not compatible with current hardware
Johnson Controls
QTY | DESCRIPTION | UNIT PRICE | TOTAL PRICE
40000 | Printed LEAF Badges | 9.03 | 361476.27 | N/A | dual frequency 26-bit and 35-bit, can work with current software and hardware, higher sequence, price includes printing for all employees | price per card

## Action Plan_old (hidden)
Date | Action | Item | Action_Owner | Audience
2023-02-16 | Mario Martinez Diaz notified Christine Wilson and Michael Draeger | Vendor notified Mario Martinez Diaz that running out of sequence on 26 bit tabs
2023-02-21 |  | Recommendations were made by the vendor to Mario Martinez Diaz
2023-02-28 | Presented Mifare DESFire EV3 - dual badge - OSS said not compatible with current software | Mario Martinez Diaz, Michael Draeger and Christine Wilson gave recommendations to OSS team | Mario Martinez Diaz, Michael Draeger and Christine Wilson | Tom Vaccarello V, Nick Georges, Desire Bayne
2023-04-13 | Presenting us with leaf badge as an option - presented pros, but cost was a factor ($9 compared to $2-3) | HR Client Services met with OSS | Michael Draeger, Christine Wilson, Mario Martinez Diaz | Nick G, Tom Vaccarello V., Desire Bayne, Connie Nie Nie, Tom Vaccarello Parker
2023-05-25 | Mario Martinez Diaz went back to Identisys to explore other options and willing to meet with OSS and Client Services |  | Mario Martinez Diaz
2023-08-08 | Vendor gave 35 bit badge as an option - could roll out slowly, but would require 2 badges until all the software updated | Group meeting (OSS, IT and Client Services) with Identisys to explore options available | Mario Martinez Diaz / Christine Wilson | Nick G, Desire Bayne, Connie Nie, Andrew, Identisys (Victoria and Tim)
2023-08-15 | Identisys gave us 35 bit badge sample for testing
2023-08-30 | More samples of 35 bit with higher sequence to test |  | Mario Martinez Diaz / Desire Bayne / Connie Nie
2023-09-03 | Confirmed new badges within scope of Idenisys - could ride Tips contract - could do slow roll out of leaf badges for employees any employee needing a replacement badge and give new leaf badges to new employees at centers starting March 2024 - order 4,400 leaf badges x $9.03 = $39,732 | Christine Wilson, Maike Dunlap and Humaira Hassan met with Finance to go over contract logistics |  | Christine Wilson / Maikle / Humaira Hassan
2023-09-20 | Gather input on leaf badges, 35 bit and decision on what is needed or funding requests and what other companies offer leaf badges | Meeting with Client Services / OSS | Mario Martinez Diaz | Mario Martinez Diaz / Christine Wilson / Maike Dunlap/ Tom Vaccarello V. / Nick Georges / Desire Bayne/ Connie Nie
2023-10-02 | Recommendations DUE from OSS, IT to Client Services on Type of Badge Needed to work with software and Hardware - decision on slow rollout or all employees. If we proceed with small rollout this year, we will need more funding for leaf badges in FY 25 budget. |  | OSS / Client Services
2023-10-04 | Follow back up with Humaira Hassan / Procurement if amendment to current contracts are needed and if more quotes are needed | Meeting - Set up | Christine Wilson / Maike Dunlap | Humaira Hassan
2023-10-06 | Request quotes from other vendors as needed |  | Mario Martinez Diaz/Desire Bayne
2023-10-20 | Quotes due back from vendors on leaf badges / other similar badges |  | Mario Martinez Diaz/Desire Bayne
2023-10-24 | Request badges from select vendors to test | Email or Meeting between OSS, IT and CS to give selected vendors | Mario Martinez Diaz | OSS, IT, CS
2023-10-30 | Vendors to provide badges to Mario Martinez Diaz |  | Mario Martinez Diaz
2023-11-09 | Deadline for OSS and IT to test vendor badges and make recommendations |  | Mario Martinez Diaz
2023-11-15 | Maike Dunlap-Funding logistics and Procurement for recommendations on amending the conttract if necessary | Come up with short/long term solution funding | Maike Dunlap | Senior Leadership - Sherry/ Marty
2023-11-20 | Submit data transfer requirements to IT - if necessary |  | Mario Martinez Diaz | IT and HRTechnogly
2023-11-20 | Submt PO to vendor |  | Mario Martinez Diaz
2023-12-01 | ORDER BADGES: Leaf Badges (6-8 weeks for printing) for arrival in March |  | Mario Martinez Diaz
2023-12-05 | Transmit data file for badges if ordering in bulk (over 20,000) - if printing inhouse, we will not need this service - ask for price adjustment |  | Joe/Allison - HR Technology
2023-02-21 | Badges arrive at Client Services |  | Mario Martinez Diaz | Client Services

## RACI Matrix
Roles and Responsibilities
Badge Rollout Matrix
R | Responsible | Individual | CEO | Director | Prin cipal | Facilities | Project Manager | Project Coordinator | Local Police | Information Management | Vendor | Internal Purchasing Team | HR | Custodians | NOTES | Suggestions / Edits
A | Accountable
C | Consulted
I | Informed
Deliverable or Task |  |  | Leadership Team |  |  |  | Core Team |  |  |  | Other Teams
Find Prox Badge |  |  |  | I |  |  | A | R |  |  | R | C | I
Badge Quotes | [6 empty] | A | R |  |  | C | C
Transfer Agreed Funds |  |  | I | R |  |  | I | I |  |  |  | R
Place Badge Order |  |  |  | I |  |  | A | R
Export Data to Vendor |  |  |  | I |  |  | A | R |  |  | C |  | R
Badge Template Export | [6 empty] | I | A
Employee Data Returned |  |  |  | I |  |  | A | R |  |  |  |  | R
Program All Badges | [6 empty] | A | R |  |  | C |  | I
Reprogram All Sites to 35-bit |  |  | I | I |  |  | A | R |  |  | R |  | I
Badge Delivery to All Sites |  |  |  | I |  |  | A | R |  |  | R | I | I
Report Missing Badges | [6 empty] | I | I |  |  | I |  | A
Print Missing Badges | [6 empty] | I | I |  |  | R |  | A
Report Badges Not Working | [6 empty] | I | I |  |  | I |  | A
Reprogram Badges Not Working | [6 empty] | A | R |  |  | I |  | I
Reconfigure All Printers | [6 empty] | A | R |  |  |  |  | I
Test Printer Functionality | [6 empty] | A | R |  |  | C |  | R
Communications |  |  | I | I |  |  | A | R |  |  | I | I | A
R | Responsible | Assigned to complete the task or deliverable.
A | Accountable | Has final decision-making authority and accountability for completion.
C | Consulted | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed | Must be informed after a decision or action.

## Project Timeline (hidden)
Project Timeline | 2023 | [16 empty] | 2024
| JAN | FEB |  |  | MAR |  | APR |  | MAY | JUN |  | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | Resposible | Status
|  | 16 | 21 | 28 | 15 | 21 | 13 | 14 | 25 | 7 | 15
Define Project Scope | [24 empty] | HR | Completed
Identify Stakeholders | [24 empty] | HR | Completed
Research | [24 empty] | All | Completed
Requirements Gathering | [24 empty] | OSS & IT | Ongoing | bar: JUL to SEP
Define Project Scope | [24 empty] | OSS & IT | Ongoing | bar: JUL to NOV
Contract Guidance | [24 empty] | HR | Planned | bar: SEP
Prox Card Identified | [24 empty] | All | Planned | bar: OCT
Submit PO | [24 empty] | HR | Planned | bar: NOV
Create Rollout Plan | [24 empty] | All | Planned | bar: DEC
Implementation | [24 empty] | All | Planned | bar: 2024 JAN to 2024 FEB